## Sheet1
See column descriptions in other tab
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | Form Requirements | 1 | H | Done | 6
2 | Form UI | 1 | H | Done | 5
3 | Make an Initial App | 1 | H | Done | 10
4 | Revise Deliverable 0 | 1 | H | Done | 5
5 | Make a Project Timeline | 1 | H | Done | 9
6 | Update Github | 1 | H | Done | 2
7 | Form Sprint Review | 1 | H | Done | 1
8 | Update Previous Documents from Deliverable 1 | 2 | H | Done | 3
9 | Complete Architecture Design Document | 2 | H | Done | 4
10 | Complete Use Case Diagrams & Descriptions | 2 | H | Done | 5
11 | Make Progress on the Application on Github | 2 | H | Done | 5
12 | Complete the SRS Document | 2,3 | H | Done | 11
13 | Revising Past Deliverables & Documents | 3 | H | Done | 7
14 | Create New Documents Meant for Deliverable 3 | 3 | H | Done | 6
15 | Setup Automatic Testing with Starting Tests | 3 | H | Done | 3
16 | As a Computer Science undergraduate, I want to search for a specific laptop by its model name so that I can make sure it suits my programming needs. | 2026-03-05 | H | Done | 11
17 | As a grandparent, I want a place to find the definitions of terms I'm unfamiliar with so that I know what kind of laptop to get my granddaughter. | 3, 4, 5 | H | Done | 7
18 | As a potential employer, I want to view info regarding the makers of a laptop catalog application so that I can know who was responsible for what and what the goals of the application is. | 2026-03-05 | H | Done | 2
19 | Update/Revise Deliv. 2 Documents | 4 | H | Done | 4
20 | Create Deliverable 4 Artifacts | 4 | H | Done | 11
21 | As an administrator, I want to be able to modify laptop entries from the site using the site’s interface so that I can quickly make edits without directly interacting with the database. | 2026-04-05 | M | Done | 11
22 | As an administrator, I want to be able to modify glossary entries using the interface so that I can ensure the site stays up-to-date with current information. | 2026-04-05 | M | Done | 5
23 | Update/Revise Previous Documents | 5 | H | Done | 11
24 | Create Final Presentation Video | 5 | H | Done | 4
25 | Complete Extra Credit Work | 5 | L | Done | 2
26 | As a busy desk worker, I want to filter by my need so I can find a laptop in SpecEffect without losing quality time that could be used elsewhere. | 5 | H | Done | 2
27 | As a user, I want to filter laptops by price so I can find a laptop that fits my budget. | 5 | H | Done | 2
28 | As a consumer, I want to view a page of information about a laptop I’m considering buying so that I know whether or not the laptop is good for basic office tasks. | 5 | H | Done | 2
29 | As a starting software developer, I want to be able to view a given device’s specifications to ensure that it fits my needs. | 5 | H | Done | 2
30 | As a consumer on borrowed time, I want to access a shortcut to view specific computer information so I don't have to waste time scrolling down to try and find it. | 5 | M | Done | 2
31 | As a consumer with trackpad issues, I want there to be a shortcut to navigate to the top of a page so that I’m not stuck having to scroll up manually. | 5 | L | Done | 1
32 | As an indecisive consumer, I want to be able to navigate back to the starting place of a website so that I can quickly start my experience from scratch when I make a decision I realize isn't helpful. | 5 | L | Done | 1
33 | Implement Miscellaneous Features | 5 | M | Done | 4
34 | As a recurring user, I want to access a shortcut that shows me laptops I’ve liked before so I don’t have to spend extra time searching for them again. | 6 | M | Backlog | 3
35 | As a user, I want to be able to save certain devices so that I can easily return to them later in a different session. | 6 | L | Backlog | 2
36 | As a tech-beginner, I want to display descriptions within SpecEffect when clicking over complex tech-vocabulary so that I can understand what each specification means without needing prior experience. | 6 | L | Backlog | 3
37 | As a person who likes to play video games, I want to open two different tabs so that I can compare the graphics of two different laptops. | 6 | M | Backlog | 1

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Priority: H (high), M (medium), L (low) o Status: Backlog, To Do, IP (in progress), QC (quality checking), D (done) o Estimate / Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.
The basic idea of story points is a story with 3 points is 3x the effort as a 1 point story, 2 points is 2x the effort, etc. In general without much experience it's hard for you to estimate relative feature sizes. Just do your best. Here's more information https://www.mountaingoatsoftware.com/blog/what-are-story-points