## Sheet1
See column descriptions in other tab
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | Form Requirements | 1 | H | Done | 6
2 | Form UI | 1 | H | Done | 5
3 | Make an Initial App | 1 | H | Done | 10
4 | Revise Deliverable 0 | 1 | H | Done | 5
5 | Make a Project Timeline | 1 | H | Done | 9
6 | Update Github | 1 | H | Done | 2
7 | Form Sprint Review | 1 | H | Done | 1
8 | Update Previous Documents from Deliverable 1 | 2 | H | Done | 3
9 | Complete Architecture Design Document | 2 | H | Done | 4
10 | Complete Use Case Diagrams & Descriptions | 2 | H | Done | 5
11 | Make Progress on the Application on Github | 2 | H | Done | 5
12 | Complete the SRS Document | 2,3,4 | H | IP | 11
13 | Revising Past Deliverables & Documents | 3 | H | Done | 7
14 | Create New Documents Meant for Deliverable 3 | 3 | H | Done | 6
15 | Setup Automatic Testing with Starting Tests | 3 | H | Done | 3
16 | As a Computer Science undergraduate, I want to search for a specific laptop by its model number so that I can make sure it suits my programming needs. | 3 | H | IP | 8
17 | As a grandparent, I want a place to find the definitions of terms I'm unfamiliar with so that I know what kind of laptop to get my granddaughter. | 3 | H | IP | 4
18 | Create About Page | 3 | H | Done | 1
19 | As a college student, I want to be able to search for and locate a laptop so that I can find a laptop that has specifications that are compatible with the programs needed to complete my degree. |  | H | Backlog | 3
20 | As a user, I want to filter laptops by price so I can find a laptop that fits my budget. |  | H | Backlog | 1
21 | As a student, I want to understand what makes a laptop perform well so that I can make informed purchasing decisions for equipment. |  | M | Backlog | 1
22 | As a starting software developer, I want to search for a laptop by its release date so that I can find an older laptop that supports legacy software. |  | M | Backlog | 2
23 | As a busy desk worker, I want to filter by my need so I can find a laptop in SpecEffect without losing quality time that could be used elsewhere. |  | H | Backlog | 2
24 | As a parent, I want to search for a laptop with a small screen size so that the laptop I get is suitable for my child’s schoolwork. |  | L | Backlog | 2
25 | As a gamer, I want to find a laptop that has specifications with good graphics so that I can get a device I know can play the newest AAA titles. |  | L | Backlog | 2
26 | As a computer enthusiast, I want to be able to view a given device’s specifications to ensure that it fits my needs. |  | H | Backlog | 2
27 | As a consumer, I want to view basic details and thumbnails of multiple devices at once in catalogue form, so that I can assess multiple options at once. |  | M | Backlog | 1
28 | As a user, I want to be able to save certain devices so that I can easily return to them later in a different session. |  | L | Backlog | 3
29 | As a person who likes to play video games, I want to open two different tabs so that I can compare the graphics of two different laptops. |  | L | Backlog | 1
30 | As a tech-beginner, I want to display descriptions within SpecEffect when hovering over complex tech-vocabulary so that I can understand what each specification means without needing prior experience. |  | M | Backlog | 3
31 | As a customer, I want to view a picture of the laptop in SpecEffect to see the shape and size of what I am potentially purchasing. |  | M | Backlog | 2
32 | As a consumer, I want to view a page of information about a laptop I’m considering buying so that I know whether or not the laptop is good for basic office tasks. |  | L | Backlog | 2
33 | As an administrator, I want to be able to modify laptop entries from the site using the site’s interface so that I can quickly make edits without directly interacting with the database. |  | M | Backlog | 4
34 | As an administrator, I want to be able to modify glossary entries using the interface so that I can ensure the site stays up-to-date with current information. |  | M | Backlog | 3

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Priority: H (high), M (medium), L (low) o Status: Backlog, To Do, IP (in progress), QC (quality checking), D (done) o Estimate / Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.
The basic idea of story points is a story with 3 points is 3x the effort as a 1 point story, 2 points is 2x the effort, etc. In general without much experience it's hard for you to estimate relative feature sizes. Just do your best. Here's more information https://www.mountaingoatsoftware.com/blog/what-are-story-points