## Sprint i
Product Backlog ID | User Story | Github Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
[9 empty] | Eliot Cole | Grace Cochran | Steven Harrington | Caramon Cotroneo
1 | Form Requirements | 43 | Write requirements for first set of features to implement | Sprint 1 | Create the basic environment for the app and describe the requirements that we must design. | KA | 1 | 1 |  |  | 100%
|  | 29 | 8-15 functional requirements |  |  | KA | 1 | 1 | 70% |  |  | 30%
|  | 55 | 8-15 functional requirements |  |  | KA | 1 | 1 |  |  | 70% | 30%
|  | 30 | 10-15 non-functional requirements |  |  | KA | 1 | 1 |  | 100%
|  | 49 | Review functional requirements |  |  | KA | 1 | 1 |  |  |  | 100%
|  | 50 | Review non functional requirements |  |  | KA | 1 | 1 |  |  |  | 100%
2 | Form UI | 31 | Make mockups of UI |  |  | KA | 2 | 2 | 30% |  | 70%
|  | 51 | Review UI mockups |  |  | KA | 1 | 1 | 100%
|  | 60 | Summary paragraph(s) of UI mockups in SRS document |  |  | KA | 1 | 1 |  | 30% |  | 70%
|  | 64 | Review paragraphs describing UI Mockups |  |  | KA | 1 | 1 |  | 100%
3 | Make an Initial App | 54 | Setup development environment |  |  | F | 1 | 1 | 100%
|  | 61 | Create basic landing page for app |  |  | F | 2 | 2 |  | 100%
|  | 63 | Add name to land page of app through code |  |  | F | 1 | 1 |  |  | 100%
|  | 62 | Add name to landing page of app |  |  | F | 1 | 1 |  |  |  | 100%
|  | 44 | Obtain snapshots or videos of the build environment working on everyone's machines |  |  | F | 1 | 1 | 25% | 25% | 25% | 25%
|  | 58 | Review snapshots or videos of the build environment |  |  | F | 1 | 1 | 100%
|  | 40 | Update README with build instructions |  |  | NF | 2 | 2 | 70% |  |  | 30%
|  | 59 | Review build instructions in README |  |  | NF | 1 | 1 |  |  |  | 100%
4 | Revise Deliverable 0 | 35 | Update user story document according to feedback [Deliverable 0] |  |  | NF | 2 | 2 |  | 70% |  | 30%
|  | 36 | Update Project Description document according to feedback [Deliverable 0] |  |  | NF | 1 | 1 |  | 70% |  | 30%
|  | 57 | Review project description document revisions [Deliverable 0] |  |  | NF | 1 | 1 |  |  |  | 100%
|  | 56 | Review user document revisions [Deliverable 0] |  |  | NF | 1 | 1 |  |  |  | 100%
5 | Make a Project Timeline | 33 | Create product backlog |  |  | KA | 2 | 2 |  | 70% | 30%
|  | 34 | Create sprint backlog |  |  | KA | 2 | 2 |  | 30% | 70%
|  | 38 | Setup Kanban board |  |  | KA | 1 | 1 |  |  |  | 100%
|  | 52 | Review product backlog |  |  | KA | 1 | 1 |  |  | 100%
|  | 53 | Review sprint backlog |  |  | KA | 1 | 1 |  | 100%
|  | 41 | Ensure product backlog and sprint backlog match |  |  | KA | 2 | 2 | 100%
6 | Update Github | 42 | update Github Repository with all documents as .pdf or .docx |  |  | KA | 2 | 2 |  |  |  | 100%
7 | Form sprint review | 39 | Create sprint review document |  |  | KA | 1 | 1 |  |  |  | 100%
8 | Update Previous Documents from Deliverable 1 | 65 | Update Project Backlog | Sprint 2 | Complete Relevant Documents and Make Progress on the Development of the Application and its Environment | KA | 1 | 1 |  | 70% |  | 30%
|  | 66 | Update Sprint Backlog |  |  | KA | 1 | 1 |  | 70% |  | 30%
|  | 72 | Update Sprint Review document with Sprint Review 2 |  |  | KA | 1 | 1 |  |  |  | 100%
9 | Complete Architecture Design Document | 75 | Make Architecture Design Diagram (UML package diagram) |  |  | KA | 2 | 2 | 70% | 30%
|  | 76 | Write design description for Architecture Design Document |  |  | KA | 2 | 2 | 70% | 30%
10 | Complete Use Case Diagrams & Descriptions | 77 | Make 2-4 use case diagrams |  |  | KA | 1 | 1 |  | 70% | 30%
|  | 78 | Write 10-20 use case descriptions |  |  | KA | 2 | 2 |  | 70% | 30%
|  | 101 | Prepare Paper Prototypes for Class Presentation |  |  | KA | 1 | 1 |  | 30% | 70%
|  | 102 | Prepare Script for Paper Prototype Presentation |  |  | KA | 1 | 1 |  | 70% |  | 30%
11 | Make Progress on the Application on Github | 79 | Begin implementation of laptop database (data cleaning, formatting, etc) |  |  | T | 2 | 2 | 70% |  |  | 30%
|  | 82 | Begin front end implementation of home page |  |  | T | 2 | 2 |  | 70% | 30%
|  | 67 | All members make at least one commit to Github |  |  | T | 1 | 1 | 25% | 25% | 25% | 25%
12 | Complete the SRS Document | 84 | Complete SRS section 1: Introduction |  |  | KA | 2 | 2 | 30% |  | 70%
|  | 86 | Complete SRS Section 2 |  |  | KA | 2 | 2 |  |  | 30% | 70%
|  | 74 | Update UI Mockups *significantly* |  |  | KA | 1 | 1 | 30% |  | 70%
|  | 85 | Complete SRS Sections 3.2, 3.3, & 3.4 |  |  | KA | 2 | 2 | 70% | 30%
|  | 83 | Complete SRS section 4: System Features |  |  | KA | 2 | 2 |  |  | 70% | 30%
|  | 88 | Complete SRS Section 5 |  |  | KA | 1 | 1 | 30% |  |  | 70%
|  | 87 | Complete SRS section 6: Other requirements |  |  | KA | 1 | 1 |  |  | 70% | 30%
13 | Revising Past Deliverables & Documents | 73 | Address Deliverable 1 Feedback | Sprint 3 | Focus on Developing the Most Important Features of the Application & Refining Previous Work | KA | 2 | 2 |  | 30% |  | 70%
|  | 121 | Revise Mockups, Use Cases, and Use Case Descriptons According to Collected Feedback |  |  | KA | 2 | 2 |  |  | 30% | 70%
|  | 104 | Update Product & Sprint Backlogs |  |  | KA | 1 | 1 |  | 70% | 30%
|  | 116 | Refine Usability Testing (Prototype) Script According to Template |  |  | KA | 1 | 1 |  |  |  | 100%
|  | 155 | Test & Revise Build Instructions for README |  |  | T | 1 | 1 | 100%
14 | Create New Documents Meant for Deliverable 3 | 111 | Create Domain Model Document |  |  | KA | 2 | 1 | 70% |  |  | 30%
|  | 112 | Create Domain Model Diagram |  |  | KA | 1 | 1 |  | 30% | 70%
|  | 115 | Create 1-10 Minute Video Showcasing the Project |  |  | KA | 3 | 3 | 40% | 20% | 20% | 20%
|  | 117 | Perform at Least 3 Prototype Tests |  |  | KA | 1 | 1 | 25% | 25% | 25% | 25%
15 | Setup Automatic Testing with Starting Tests | 114 | Setup Continuous Integration on Github |  |  | NF, T | 2 | 2 | 30% |  |  | 70%
|  | 149 | Write basic starter tests to be committed to main branch. |  |  | NF, T | 1 | 1 |  |  |  | 100%
16 | As a Computer Science undergraduate, I want to search for a specific laptop by its model number so that I can make sure it suits my programming needs. | 126 | Add Laptop Data to Database |  |  | F, T | 3 | 3 | 100%
|  | 128 | Create Component For Search Results |  |  | F, T | 3 | 3 |  | 30% | 70%
17 | As a grandparent, I want a place to find the definitions of terms I'm unfamiliar with so that I know what kind of laptop to get my granddaughter. | 125 | Write Content Text For Glossary Page |  |  | F, T | 2 | 2 |  | 30% |  | 70%
|  | 129 | Create Frontend UI For Glossary Page |  |  | F, T | 2 | 2 | 30% | 70%
18 | Create About Page | 124 | Begin implementation of About Page |  |  | F, T | 1 | 1 |  | 30% | 70%
?? |  | 103 | Break Deliverable 2 Feedback into Revision Tasks | Sprint 4 |  | KA | 1

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657